## Work Units
Work Unit	V1|2|3	Feb Est (hrs)	Feb Act	Hrs: 4/20 Est				Est Δ		Hrs: 5/22 Act		%		Feb Notes	Run'g Est	Progr's	4/20 Notes	Priority
				Σ	V1	V2	V3			Σ	Δ

Cycloplan (Cyclopath V1+V2)		0.00			144.00	182.25	3.00	182.25				100%		Cyclopath Version 100 (i.e., V2; V3 will be Version 1000).		100%

Flashclient	V1	x		x				#VALUE!				100%				100%
Gatekeeper	V1	x		x				#VALUE!				100%		Probably okay		100%
Log In	V1	x		x				#VALUE!				100%				100%
Log In [Dialog]	V1	0.00		0.0	0.00			0.00		0.0	0.0	100%			0.00	100%
Sign Up [Wiki]	V1	0.00		0.0	0.00			0.00		0.0	0.0	100%			0.00	100%
Privacy Policy [Wiki; Pink is Private]	V1	0.00		0.0	0.00			0.00		0.0	0.0	100%			0.00	100%
Forgot Password [Wiki]	V1	0.00		0.0	0.00			0.00		0.0	0.0	100%			0.00	100%
Preserve Session	V1	0.00		2.5	2.50			0.00		1.3	0.5	50%			2.50	50%
Log Out	V1	x		x				#VALUE!				100%				100%
Unsaved Changes [Prompt]	V1	0.00		0.0	0.00			0.00		0.0	0.0	100%			0.00	100%
Cleanup Session	V1	0.00		0.5	0.50			0.00		0.0	0.0	0%			0.50	0%
Banner Tab Panels	V2	x		x				#VALUE!				100%				100%
Maps	V2	x		x				#VALUE!				100%				100%
All My Maps	V2	0.00		x				#VALUE!				100%				100%
Branch List	V2	x		x				#VALUE!				100%				100%
GWIS Get	V2	0.00		2.0		2.00		2.00				100%				100%
Branch List	V2	0.00		2.0		2.00		2.00				100%				100%
Activate Branch	V2	0.00		4.0		4.00		4.00				100%				100%
Learn More [Wiki]	V2	0.00		1.0		1.00		1.00				100%				100%
Create Branch	Vn	0.00		0.0			0.00	0.00				100%				100%
Copy Branch	V2	0.00		3.0		3.00		3.00				100%				100%
Merge Branch	V2	0.00		4.0		4.00		4.00				100%				100%
Import Branch	Vn	0.00		0.0		0.00		0.00				100%				100%
Export Branch	Vn	0.00		0.0		0.00		0.00				100%				100%
Pagination	V3	0.00		3.0			3.00	0.00				100%				100%
Help [Panel]	V1	x		x				#VALUE!				100%				100%
Icons and Text	V1	0.00		0.0	0.00			0.00				100%				100%
Side Panel Tabs	V1	x		x				#VALUE!				100%				100%
Side Panel Infrastructure	V1	x		x				#VALUE!				100%				100%
Side Panel Classes	V2	0.00		1.0		1.00		1.00				100%		Probably okay; test it		100%
Detail Panels Classes	V2	0.00		1.0		1.00		1.00				100%		Probably okay; test it		100%
Tab Navigator Icons/Tab Control	V1	0.00		0.0	0.00			0.00				100%		Probably okay; test it		100%
Inter-Panel Nav, e.g., “Top » Current”	V2	0.00		0.5		0.50		0.50				100%		Probably okay; test it		100%
Routes	V1	x		x				#VALUE!				100%				100%
Find Route (Dialog)	V1	x		x				#VALUE!				100%		Probably okay; test it		100%
GWIS Get	V1	0.00		7.0	7.00			0.00				100%				100%
Basics: From/To, Restore Defaults	V1	0.00		1.0	1.00			0.00				100%				100%
Tag Preferences	V1	x		x				#VALUE!				100%				100%
Rating Slider	V1	0.00		1.0	1.00			0.00				100%		Finish Testing		100%
Tag Prefs Widget	V1	0.00		1.0	1.00			0.00				100%		Finish Testing		100%
Save Settings	V1	0.00		1.0	1.00			0.00				100%		Finish Testing		100%
Finding Route Dialog.......	V1	0.00		1.0	1.00			0.00				100%				100%
Routes List	V1	x		x				#VALUE!				100%		Probably okay; test it		100%
Basics: Clickable, Hide Old, All|None|Clear	V1	0.00		1.0	1.00			0.00				100%		Probably okay; test it		100%
Routes List	V1	x		x				#VALUE!				100%		Probably okay; test it		100%
Routes List	V1	0.00		1.0	1.00			0.00				100%		Finish Testing		100%
Look-at	V1	0.00		1.0	1.00			0.00				100%		Finish Testing		100%
Route Details	V1	0.00		1.0	1.00			0.00				100%		Finish Testing		100%
Delete Route [from client]	V1	0.00		1.0	1.00			0.00				100%		Finish Testing		100%
Route Details	V1	x		x				#VALUE!				100%		Probably okay; test it		100%
Basics: Panel Design	V1	0.00		1.0	1.00			1.00				100%				100%
Feedback on this Route	V1	0.00		1.0	1.00			1.00				100%				100%
Create Link	V1	0.00		1.0	1.00			1.00				100%				100%
Color Route By	V1	0.00		1.0	1.00			1.00				100%				100%
Cue Sheet	V1	0.00		1.0	1.00			1.00				100%				100%
Printer Friendly	V1	0.00		1.0	1.00			1.00				100%				100%
As GPX	V1	0.00		1.0	1.00			1.00				100%				100%
Items	V1	x		x				#VALUE!				100%				100%
Class Design	V2	x		x				#VALUE!				100%		Cleanup / Test Tags, Attachments, Discussions / GUI Tweaks (I think Basic Tab needs veritcal scrollbar for smaller monitors)		100%
Item Versioned Classes	V2	x		1.0		1.00		#VALUE!				100%				100%
Group Access Classes	V2	x		4.0		4.00		#VALUE!				100%				100%
Item Class Design	V2	0.00		1.0		1.00		1.00				100%		Code cleanup / Conf setting to hide new panels		100%
Panels and Widgets	V2	x		x				#VALUE!				100%		Cleanup / Test Tags, Attachments, Discussions / GUI Tweaks (I think Basic Tab needs veritcal scrollbar for smaller monitors)		100%
Panel Class Design	V2	x		0.0		0.00		#VALUE!				100%				100%
Basic [Tab]	V2	x		x				#VALUE!				100%				100%
Item Name [Label]	V1	0.00		0.0	0.00			0.00				100%		Finish Testing		100%
Extra [Tab]	V2	x		x				#VALUE!				100%				100%
Email Updates	V2	0.00		2.0		2.00		2.00				100%		Finish Testing		100%
Edit Attributes	V1	x		x				#VALUE!				100%		Finish Testing		100%
GWIS Get	V2	0.00		1.0		1.00		1.00				100%				100%
Attributes List	V1	0.00		1.0	1.00			1.00				100%				100%
Custom Widgets	V1	0.00		0.0	0.00			0.00				100%				100%
Delete Item	V1	0.00		2.0	2.00			2.00				100%		Finish Testing		100%
Groups [Tab]	V2	x		x				#VALUE!				100%				100%
User's Access [Label]	V2	0.00		0.0		0.00		0.00				100%		Finish Testing		100%
Item Scope [Label]	V2	0.00		0.0		0.00		0.00				100%		Finish Testing		100%
Group Access List	V2	x		x				#VALUE!				100%		Finish Testing		100%
GWIS Get	V2	0.00		4.0		4.00		4.00				100%				100%
GWIS Put	V2	0.00		4.0		4.00		4.00				100%				100%
Group Access List	V2	0.00		1.0		1.00		1.00				100%				100%
Access Level Control	V2	0.00		1.0		1.00		1.00				100%				100%
Delete/Deny Access	V2	0.00		1.0		1.00		1.00				100%				100%
Make Public	V2	0.00		2.0		2.00		2.00				100%				100%
Make Private Copy	V2	0.00		2.0		2.00		2.00				100%				100%
Add User or Group	V2	0.00		4.0		4.00		4.00				100%				100%
Learn More [Wiki]	V2	0.00		1.0		1.00		1.00				100%				100%
Geofeature Panels	V1	x		x				#VALUE!				100%		Cleanup / Test Tags, Attachments, Discussions / GUI Tweaks (I think Basic Tab needs veritcal scrollbar for smaller monitors)		100%
Basic [Tab]	V2	x		x				#VALUE!				100%				100%
Tags	V1	x		x				#VALUE!				100%		Finish Testing		100%
Show Tags	V1	0.00		0.3	0.25			0.25				100%				100%
Add Tag	V1	0.00		0.3	0.25			0.25				100%				100%
Delete Tag	V1	0.00		0.3	0.25			0.25				100%				100%
Tags Help [Wiki]	V1	0.00		0.0	0.00			0.00				100%				100%
Rating	V1	x		x				#VALUE!				100%		Finish Testing		100%
GWIS Get	V1	0.00		1.0	1.00			1.00				100%				100%
GWIS Put	V1	0.00		1.0	1.00			1.00				100%				100%
Show User's	V1	0.00		0.3	0.25			0.25				100%				100%
Show Estimate	V1	0.00		0.0	0.00			0.00				100%				100%
Ratings Help [Wiki]	V1	0.00		0.0	0.00			0.00				100%				100%
Discussions	V1	x		x				#VALUE!				100%		Finish Testing		100%
Start New	V1	0.00		1.0	1.00			1.00				100%				100%
See Existing	V1	0.00		1.0	1.00			1.00				100%				100%
Notes	V1	x		x				#VALUE!				100%		Finish Testing		100%
Show Notes	V1	0.00		0.0	0.00			0.00				100%				100%
Add Note	V1	0.00		0.0	0.00			0.00				100%				100%
Edit Note	V1	0.00		0.0	0.00			0.00				100%				100%
Delete Note	V1	0.00		0.0	0.00			0.00				100%				100%
Extra [Tab]	V2	x		x				#VALUE!				100%				100%
Item Type	V1	0.00		0.0	0.00			0.00				100%		Finish Testing		100%
Branch Panels	V2	x		x				#VALUE!				100%		Code cleanup / Conf setting to hide new panels		100%
Extra [Tab]	V2	x		x				#VALUE!				100%				100%
Manage Attributes	V2	x		x				#VALUE!				100%		Finish Testing		100%
Add New Attribute	V2	0.00		1.0		1.00		1.00				100%				100%
Edit Attribute	V2	0.00		1.0		1.00		1.00				100%				100%
Move Up/Down in List	Vn	0.00		0.0			0.00	0.00				100%				100%
Delete Attribute	V2	0.00		0.3		0.25		0.25				100%				100%
Branch Conflicts [Tab]	V2	x		x				#VALUE!				100%				100%
Conflicts List	V2	x		x				#VALUE!				100%				100%
GWIS Get	V2	0.00		2.0		2.00		2.00				100%				100%
GWIS Put	V2	0.00		4.0		4.00		4.00				100%				100%
Conflicts List	V2	0.00		2.0		2.00		2.00				100%				100%
Zoom To	V2	0.00		1.0		1.00		1.00				100%				100%
Read Diff	V2	0.00		8.0		8.00		8.00				100%				100%
Keep Mine	V2	0.00		1.0		1.00		1.00				100%				100%
Discard Mine	V2	0.00		1.0		1.00		1.00				100%				100%
Reload [Update Branch]	V2	0.00		1.0		1.00		1.00				100%				100%
Learn More [Wiki]	V2	0.00		1.0		1.00		1.00				100%				100%
Select All | Select None	V2	0.00		0.5		0.50		0.50				100%				100%
Pagination	Vn	0.00		0.0			0.00	0.00				100%				100%
New Item Policy [Tab]	Vn	0.00		0.0			0.00	0.00				100%				100%
Byway Panel	V1	x		x				#VALUE!				100%		Code cleanup / Conf setting to hide new panels		100%
Extra [Tab]	V1	x		x				#VALUE!				100%				100%
Merge Items [Applies to: Byway]	V1	0.00		1.0	1.00			1.00				100%		Finish Testing		100%
Annotation Panel	V1	x		x				#VALUE!				100%		Code cleanup / Conf setting to hide new panels		100%
Basic [Tab]	V2	x		x				#VALUE!				100%				100%
Edit Comments	V1	0.00		0.0	0.00			0.00				100%				100%
Extra [Tab]	V2	x		x				#VALUE!				100%				100%
Add To	V1	0.00		0.0	0.00			0.00				100%				100%
Remove From	V1	0.00		0.0	0.00			0.00				100%				100%
Attribute Panel	V2	x		x				#VALUE!				100%		Code cleanup / Conf setting to hide new panels		100%
Basic [Tab]	V2	x		x				#VALUE!				100%				100%
Value Type	V2	0.00		0.0		0.00		0.00				100%				100%
Multiple Okay	V2	0.00		0.0		0.00		0.00				100%				100%
Hints & Units	V2	0.00		0.0		0.00		0.00				100%				100%
Appies To	V2	0.00		0.0		0.00		0.00				100%				100%
Settings	V1	x		x				#VALUE!				100%				100%
Options [Tab]	V2	x		x				#VALUE!				100%		Probably okay; test it		100%
Connectivity	V1	0.00		0.0	0.00			0.00				100%				100%
Tooltips on Blocks	V1	0.00		0.0	0.00			0.00				100%				100%
Regions	V1	0.00		0.0	0.00			0.00				100%				100%
Sticky Intersections	V1	0.00		0.0	0.00			0.00				100%				100%
Aerial Photos	V1	0.00		0.0	0.00			0.00				100%				100%
Aerial: Vector Transparency	V1	0.00		0.0	0.00			0.00				100%				100%
Tag Filter List [Tab]	V2	x		x				#VALUE!				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Tag Filter List	V1	0.00		0.0	0.00			0.00				100%				100%
Check All, Check None	V1	0.00		0.0	0.00			0.00				100%				100%
User Account [Tab]	Vn	x		x				#VALUE!				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Email Digest/Immediate	Vn	0.00		0.0			0.00	0.00				100%				100%
Search	V1	x		x				#VALUE!				100%		Probably okay		100%
GWIS Command	V1	0.00		8.0	8.00			8.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Filter Options	V1	0.00		0.0	0.00			0.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Results List	V1	x		x				#VALUE!				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Populate List	V1	0.00		0.0	0.00			0.00				100%				100%
Look At	V1	0.00		0.0	0.00			0.00				100%				100%
Route from | to	V1	0.00		0.0	0.00			0.00				100%				100%
Load Historic Revision	V1	0.00		0.0	0.00			0.00				100%				100%
Pagination [Next|Prev]	V1	0.00		0.0	0.00			0.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Pagination [<< < n of m > >>]	Vn	0.00		0.0			0.00	0.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Panel Misc. (Clear button)	V1	0.00		0.0	0.00			0.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
More Info [Wiki]	V1	0.00		0.0	0.00			0.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Discussions	V1	x		x				#VALUE!				100%		Fix item_put problem / Use new item class / Use new map update		100%
GWIS Command	V1	0.00		4.0	4.00			4.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Filter Options	V1	0.00		0.0	0.00			0.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Mark All As Read	V1	x		x				#VALUE!				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
GWIS Item_Reader Command	V1	0.00		1.0	1.00			1.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Start New Thread	V1	x		x				#VALUE!				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
GWIS Command	V1	0.00		2.0	2.00			2.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Edit Title and Post Body	V1	0.00		1.0	1.00			1.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Attach Selected Items	V1	0.00		1.0	1.00			1.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
More Info [Wiki]	V1	0.00		0.0	0.00			0.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
My Watched Items	V1	x		x				#VALUE!				100%		Use new item class / Test item_get (already coded) / Fix: item_put		100%
GWIS Command	V1	0.00		2.0	2.00			2.00				100%				100%
Watched Item List	V1	x		x				#VALUE!				100%				100%
Look-at	V1	0.00		1.0	1.00			1.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Details	V1	0.00		1.0	1.00			1.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Email Notification of Changes	V1	0.00		1.0	1.00			1.00				100%				100%
Help Docs	V1	x		x				#VALUE!				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Panel Text and Icon	V1	0.00		0.0	0.00			0.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
More Info [Wiki]	V1	0.00		0.0	0.00			0.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Recent Changes	V1	x		x				#VALUE!				100%				100%
Changes Filter Options	V1	0.00		1.0	1.00			1.00				100%		Incl. Filter Changes, Search By User, etc.		100%
Revert Revisions	V1	0.00		3.0	3.00			3.00				100%		Incl. Filter Changes, Search By User, etc.		100%
Write Feedback	V1	0.00		1.0	1.00			1.00				100%		Incl. Filter Changes, Search By User, etc.		100%
Pagination [Show latest n revisions]	V1	0.00		0.0	0.00			0.00				100%		Incl. Filter Changes, Search By User, etc.		100%
Pagination [<< < n of m > >>]	Vn	0.00		0.0			0.00	0.00				100%		Used new item classes, but probably okay / Fix: GUI panel falls below Control Panel		100%
Changes List	V1	0.00		2.0	2.00			2.00				100%		Incl. Filter Changes, Search By User, etc.		100%
Show Historic Rev in Map and Panels	V1	x		x				#VALUE!				100%				100%
Load Historic Revision	V1	0.00		3.0	3.00			3.00				100%				100%
Change Details Panel State	V1	0.00		3.0	3.00			3.00				100%				100%
Show Diffed Revs in Map and Panels	V1	x		x				#VALUE!				100%				100%
Load Three Revs (new, old, static)	V1	0.00		3.0	3.00			3.00				100%		Test getting and loading the three revs (new, old, static)		100%
Change Details Panel State	V1	0.00		3.0	3.00			3.00				100%		Fix: Details panels diffs (this is the time consuming part)		100%
Map Canvas	V1	x		x				#VALUE!				100%				100%
GWIS Checkout	V2	0.00		4.0		4.00						100%				100%
Tiles (Incl. Aerial)	V1	0.00		0.0	0.00			0.00				100%		Works		100%
Editing Tools	V1	x		x				#VALUE!				100%		Commands are already coded to use new item class, mostly just need to test		100%
Floating Palette	V1	0.00		0.0	0.00			0.00				100%				100%
Tool Classes	V1	x		x				#VALUE!				100%				100%
Class Design	V1	0.00		1.0	1.00			1.00				100%		Fix: Details panels diffs (this is the time consuming part)		100%
Zoom and Pan	V1	0.00		1.0	1.00			1.00				100%		Fix: Details panels diffs (this is the time consuming part)		100%
Doubleclick handler	V2	0.00		1.0		1.00		1.00				100%		Fix: Details panels diffs (this is the time consuming part)		100%
Enable/Disable Tools per User Access	V2	0.00		0.0		0.00		0.00				100%		Fix: Details panels diffs (this is the time consuming part)		100%
Editing How-To [Wiki]	V1	0.00		0.0	0.00			0.00				100%		Fix: Details panels diffs (this is the time consuming part)		100%
Cmd Mgr [Undo/Redo]	V1	0.00		0.0	0.00			0.00				100%		Probably okay		100%
Save Changes (& Discard)	V1	0.00		0.0	0.00			0.00				100%		Probably okay		100%
Mouse Handler	V1	x		x				#VALUE!				100%		Works		100%
Zoom and Pan	V1	0.00		0.0	0.00			0.00				100%		Fix: Details panels diffs (this is the time consuming part)		100%
Doubleclick handler	V2	0.00		0.0		0.00		0.00				100%		Fix: Details panels diffs (this is the time consuming part)		100%
Compass Rose	V1	x		x				#VALUE!				100%		i.e., Geofeatures, Highlights, Shadows, Tiles / Seems to work, but need to compare against V1 and make sure I didn't break anything		100%
Pan Arrows	V1	0.00		0.0	0.00			0.00				100%		Probably okay		100%
Throbber	V1	0.00		0.0	0.00			0.00				100%		Probably okay		100%
Pan Arrows	V1	0.00		0.0	0.00			0.00				100%		Probably okay		100%
View Stack Chevrons	V1	0.00		0.0	0.00			0.00				100%		i.e., Geofeatures, Highlights, Shadows, Tiles / Seems to work, but need to compare against V1 and make sure I didn't break anything		100%
Search Button	V1	x		x				#VALUE!				100%		i.e., Geofeatures, Highlights, Shadows, Tiles / Seems to work, but need to compare against V1 and make sure I didn't break anything		100%
Convert to Search Box	Vn	0.00		0.0			0.00	0.00				100%		i.e., Geofeatures, Highlights, Shadows, Tiles / Seems to work, but need to compare against V1 and make sure I didn't break anything		100%
Mode Selector (View-mode, Edit-mode)	Vn	0.00		0.0			0.00	0.00				100%		i.e., Geofeatures, Highlights, Shadows, Tiles / Seems to work, but need to compare against V1 and make sure I didn't break anything		100%
Tiles (Incl. Aerial)	V1	0.00		0.0	0.00			0.00				100%		Works		100%
Map Key	V1	x		x				#VALUE!				100%		i.e., Geofeatures, Highlights, Shadows, Tiles / Seems to work, but need to compare against V1 and make sure I didn't break anything		100%
Make More Hideable	V2	0.00		0.0		0.00		0.00				100%		Probably okay		100%
Scale Widget	V1	0.00		0.0	0.00			0.00				100%		i.e., Geofeatures, Highlights, Shadows, Tiles / Seems to work, but need to compare against V1 and make sure I didn't break anything		100%
Map Widgets	V1	x		x				#VALUE!				100%		i.e., Geofeatures, Highlights, Shadows, Tiles / Seems to work, but need to compare against V1 and make sure I didn't break anything		100%
Pointing Widget	V1	0.00		0.0	0.00			0.00				100%		Probably okay		100%
Support Packages	V1	0.00		x	0.00			0.00				100%		Finish coding new map canvas update classes / Test pan/zoom, change rev/branch/user / Skip: test rev browser, discussions, routes (See their Panels for the workpackage) / For working copy update, don't add to Branch Conflicts panel, just assume working copy item wins and bump version so it saves		100%
m4 Preprocessor	V1	x		x				#VALUE!				100%		i.e., Geofeatures, Highlights, Shadows, Tiles / Seems to work, but need to compare against V1 and make sure I didn't break anything		100%
Basics: makefile, m4_DEBUG*, m4_ASSERT	V1	0.00		0.0	0.00			0.00				100%		Read from new group_revision table according to user and group memberships		100%
Free (Release) vs. Checked (Debug) Build	V2	0.00		0.0		0.00		0.00				100%		Read from new group_revision table according to user and group memberships		100%
Log/Trace Facility	V2	0.00		0.0		0.00		0.00				100%		i.e., Geofeatures, Highlights, Shadows, Tiles / Seems to work, but need to compare against V1 and make sure I didn't break anything		100%
Network Stack	V2	0.00		2.0		2.00		2.00				100%		i.e., Geofeatures, Highlights, Shadows, Tiles / Seems to work, but need to compare against V1 and make sure I didn't break anything		100%
utils.misc Package	V1/2	0.00		0.0	0.00			0.00				100%		i.e., Geofeatures, Highlights, Shadows, Tiles / Seems to work, but need to compare against V1 and make sure I didn't break anything		100%
												100%				100%
Pyserver	V1	x		x				#VALUE!				100%				100%
GWIS Commands	V1	x		x				#VALUE!				100%				100%
Geocode	V1	0.00		4.0	4.00			4.00				100%		Need to integrate Fernado's search code / Need to edit code to use V2 / SQL is complicated and touchy, buffering time for unknowns		100%
Checkout	V1	x		x				#VALUE!				100%		Getting current version seems to be working / Need to test historic and diff fetches; fairly confident it works (and fairly confident SQL fix would be easyish)		100%
Public Branch	V1	0.00		0.0	0.00			0.00				100%		Read from new group_revision table according to user and group memberships		100%
Any Branch	V2	0.00		0.0		0.00		0.00				100%		Read from new group_revision table according to user and group memberships		100%
Performance Issues	V2	0.00		16.0		16.00		16.00		16.00		100%		Read from new group_revision table according to user and group memberships		100%
Commit	V1	x		x				#VALUE!				100%		Python and SQL changes / Needs to work with new item class / Needs to work with new group access control / For each existing item being saved, check that user has rights via group_item_access.access_level / For each new item being saved, check user has rights via new_item_policy, and set new items permissions accordingly, then appy client-supplied permissions, checking permissions once again (so two steps: create item, then save item like it's an existing item)		100%
Save Public Branch Items	V1	0.00		4.0	4.00			4.00				100%		Read from new group_revision table according to user and group memberships		100%
Save Any Branch Items	V2	0.00		4.0		4.00		4.00				100%		Read from new group_revision table according to user and group memberships		100%
Save Group Access Permissions	V2	0.00		4.0		4.00		4.00				100%		Read from new group_revision table according to user and group memberships		100%
Ratings	V1	0.00		1.0	1.00			1.00				100%		Read from new group_revision table according to user and group memberships		100%
Item Watchers	V1	x		x				#VALUE!				100%		Read from new group_revision table according to user and group memberships		100%
Regions	V1	0.00		1.0	1.00			1.00				100%		Read from new group_revision table according to user and group memberships		100%
Any Item Type	V2	0.00		1.0		1.00		1.00				100%		Read from new group_revision table according to user and group memberships		100%
Item Readers	V1	x		x				#VALUE!				100%		Read from new group_revision table according to user and group memberships		100%
Threads/Posts	V1	0.00		1.0	1.00			1.00				100%		Read from new group_revision table according to user and group memberships		100%
Any Item Type	V2	0.00		1.0		1.00		1.00				100%		Read from new group_revision table according to user and group memberships		100%
Branches	V2	x		x				#VALUE!				100%		Python and SQL changes / Needs to work with new item class / Needs to work with new group access control / For each existing item being saved, check that user has rights via group_item_access.access_level / For each new item being saved, check user has rights via new_item_policy, and set new items permissions accordingly, then appy client-supplied permissions, checking permissions once again (so two steps: create item, then save item like it's an existing item)		100%
Create Branch	V3	0.00		0.0			0.00	0.00				100%		Read from new group_revision table according to user and group memberships		100%
Merge Two Branches	V2	0.00		4.0		4.00		4.00				100%		Read from new group_revision table according to user and group memberships		100%
Update Branch	V2	0.00		4.0		4.00		4.00				100%		Read from new group_revision table according to user and group memberships		100%
Export Branch	Vn	0.00		0.0			0.00	0.00				100%		Read from new group_revision table according to user and group memberships		100%
Import Branch	Vn	0.00		0.0			0.00	0.00				100%		Read from new group_revision table according to user and group memberships		100%
Revision History	V1	x		x				#VALUE!				100%				100%
Get History	V1	0.00		2.0	2.00			2.00				100%		Read from new group_revision table according to user and group memberships		100%
Revert Revision	V1	0.00		2.0	2.00			2.00				100%		Check group permissions / Revert only items for which user has editor access / Create new revision according to what was reverted and what wasn't, and create for appropriate groups		100%
Put Feedback	V1	0.00		0.0	0.00			0.00				100%		Nothing really changed, just need to test		100%
Route	V1	0.00		0.0	0.00			0.00				100%		Get Route, Put Feedback, Share Route / Get Route uses routed, so should be okay / Put Feedback should use new SQL, but should be simple / Share Route should use new group access permissions (check user has rights to edit, update group_item_access); can hopefully use new item_put code to do this		100%
Thread	V1	0.00		0.0	0.00			0.00				100%		Should use item_get instead / Get rid of thread_get and use item_versioned's thread.py class		100%
User	V1	0.00		0.0	0.00			0.00				100%		Seems to be working		100%
Group Access Get	V2	0.00		0.0		0.00		0.00				100%		Return list of groups and access_level for user at requested revisions		100%
New Item Policy Get	V2	0.00		0.0		0.00		0.00				100%		Return new item policy list for user at requesed revision for branch		100%
Watcher Emails	V1	0.00		4.0	4.00			4.00				100%		Send watch item emails / Use new database schema		100%
												100%				100%
Route Daemon (routed)	V1	x		x				#VALUE!				100%		tgraph and route_finder need to use new database model / Complicated SQL / Need to fetch attributes link values, which is new code / Takes a while to load routed and to test changes (routed takes 30+ sec. to boot, probably now because of separate attribute link_value fetches)		100%
Route Using Public Map	V1	0.00		8.0	8.00			8.00				100%		Code cleanup / I wrote lots of FIXMEs but that was when I was understanding the problem; I think most are done or obsolete or no-ops, but I still want to check them all / Buffering a little time in case something is wrong and I have to fix the schema update scripts / It can take all night long to run the update scripts, so it takes a while to test changes / I'm not as keen on archiving the existing tables, since it seems to leave cruft (e.g., it you archive a table, some fcns. in the public schema still point to it) / Note sure what the solution is: probably can just clean it up later, I can't think of a good solution that's easy and not risky		100%
Route Using Any Branch	V2	0.00		8.0		8.00		8.00				100%		Code cleanup / I wrote lots of FIXMEs but that was when I was understanding the problem; I think most are done or obsolete or no-ops, but I still want to check them all / Buffering a little time in case something is wrong and I have to fix the schema update scripts / It can take all night long to run the update scripts, so it takes a while to test changes / I'm not as keen on archiving the existing tables, since it seems to leave cruft (e.g., it you archive a table, some fcns. in the public schema still point to it) / Note sure what the solution is: probably can just clean it up later, I can't think of a good solution that's easy and not risky		100%
												100%				100%
TileCache	V1	0.00		0.0	0.00			0.00				100%		Seems to be working / I updated SQL to fetch most recent revision of items from Public Branch for Anonymous User		100%
												100%				100%
MapServer	V1	0.00		6.0	6.00			6.00				100%		Seems to be working		100%
												100%				100%
Scripts	V1	x		x				#VALUE!				100%				100%
SQL	V1	0.00		16.0	16.00			16.00		16.00		100%		Code cleanup / I wrote lots of FIXMEs but that was when I was understanding the problem; I think most are done or obsolete or no-ops, but I still want to check them all / Buffering a little time in case something is wrong and I have to fix the schema update scripts / It can take all night long to run the update scripts, so it takes a while to test changes / I'm not as keen on archiving the existing tables, since it seems to leave cruft (e.g., it you archive a table, some fcns. in the public schema still point to it) / Note sure what the solution is: probably can just clean it up later, I can't think of a good solution that's easy and not risky		100%
Auditor	V1	0.00		8.0	8.00			8.00				100%		300 lines of SQL needs to be updated		100%
Cron	V1	0.00		4.0	4.00			4.00				100%		Mirroring public repository has a problem w/ permissions/ssh running from landonb's account		100%
Usage	V1	0.00		0.0	0.00			0.00				100%		The SQL used to make the gnuplots needs to be updated / Looks fairly straight-forward / Should also test / I'm not sure if a cron job runs this or what		100%
Watcher Emails	V1	0.00		4.0	4.00			4.00				100%		Test cron job / Test calling new item class		100%
Misc	V1	0.00		0.0	0.00			0.00				100%		Go through remaining script in the directory and see what else needs updating		100%
Branches	V2	x		x				#VALUE!				100%		Python and SQL changes / Needs to work with new item class / Needs to work with new group access control / For each existing item being saved, check that user has rights via group_item_access.access_level / For each new item being saved, check user has rights via new_item_policy, and set new items permissions accordingly, then appy client-supplied permissions, checking permissions once again (so two steps: create item, then save item like it's an existing item)		100%
Create Branch	V2	0.00		2.0		2.00		2.00				100%		Read from new group_revision table according to user and group memberships		100%
Copy Branch	V2	0.00		2.0		2.00		2.00				100%		Read from new group_revision table according to user and group memberships		100%
Merge Branches	V2	0.00		4.0		4.00		4.00				100%		Read from new group_revision table according to user and group memberships		100%
Import Branch	V2	0.00		3.0		3.00		3.00				100%		Read from new group_revision table according to user and group memberships		100%
Export Branch	V2	0.00		3.0		3.00		3.00				100%		Read from new group_revision table according to user and group memberships		100%
Groups	V2	x		x				#VALUE!				100%		Python and SQL changes / Needs to work with new item class / Needs to work with new group access control / For each existing item being saved, check that user has rights via group_item_access.access_level / For each new item being saved, check user has rights via new_item_policy, and set new items permissions accordingly, then appy client-supplied permissions, checking permissions once again (so two steps: create item, then save item like it's an existing item)		100%
Create Group	V2	0.00		0.0		0.00		0.00				100%		Read from new group_revision table according to user and group memberships		100%
Update Memberships	V2	0.00		0.0		0.00		0.00				100%		Read from new group_revision table according to user and group memberships		100%
												100%				100%
GIS Export [Automated, e.g., nightly]	V2	0.00		8.0		8.00		8.00				100%		Seems to be working		100%
												100%				100%
Route Analytics	V2	0.00		24.0		24.00		24.00				100%		Seems to be working		100%
												100%				100%
MetCouncil + Cyclopath Conflation	V2	0.00		x				#VALUE!				100%		Seems to be working		100%
Audit OpenJump Data	V2	0.00		4.0		4.00		4.00				100%		Python and SQL changes / Needs to work with new item class / Needs to work with new group access control / For each existing item being saved, check that user has rights via group_item_access.access_level / For each new item being saved, check user has rights via new_item_policy, and set new items permissions accordingly, then appy client-supplied permissions, checking permissions once again (so two steps: create item, then save item like it's an existing item)		100%
SQL Import Scripts	V2	0.00		8.0		8.00		8.00				100%		Python and SQL changes / Needs to work with new item class / Needs to work with new group access control / For each existing item being saved, check that user has rights via group_item_access.access_level / For each new item being saved, check user has rights via new_item_policy, and set new items permissions accordingly, then appy client-supplied permissions, checking permissions once again (so two steps: create item, then save item like it's an existing item)		100%
Audit Imported Data	V2	0.00		4.0		4.00		4.00				100%		Python and SQL changes / Needs to work with new item class / Needs to work with new group access control / For each existing item being saved, check that user has rights via group_item_access.access_level / For each new item being saved, check user has rights via new_item_policy, and set new items permissions accordingly, then appy client-supplied permissions, checking permissions once again (so two steps: create item, then save item like it's an existing item)		100%
												100%				100%
Testing	V2	x		x				#VALUE!				100%				100%
Functional Testing	V2	0.00		0.0		0.00		0.00				100%				100%
User Testing	V2	0.00		0.0		0.00		0.00				100%				100%
												100%				100%
Code Review	V2	x		x				#VALUE!				100%				100%
Flashclient Classes	V2	x		x				#VALUE!				100%				100%
Items	V2	0.00		0.0		0.00		0.00				100%				100%
Map Canvas and Update	V2	0.00		0.0		0.00		0.00				100%				100%
Command and Tool	V2	0.00		0.0		0.00		0.00				100%				100%
dpanels and mxml	V2	0.00		0.0		0.00		0.00				100%				100%
Network and GWIS	V2	0.00		0.0		0.00		0.00				100%				100%
Package Structure and Style	V2	0.00		0.0		0.00		0.00				100%				100%
Pyserver	V2	x		x				#VALUE!				100%				100%
GWIS and command	V2	0.00		0.0		0.00		0.00				100%				100%
Item	V2	0.00		0.0		0.00		0.00				100%				100%
Package Structure and Style	V2	0.00		0.0		0.00		0.00				100%				100%
Database	V2	0.00		x		0.00		0.00				100%				100%
New Schema [Design]	V2	0.00		0.0		0.00		0.00				100%				100%
Upgrade Scripts [SQL]	V2	0.00		0.0		0.00		0.00				100%				100%
Scripts	V2	0.00		0.0		0.00		0.00				100%				100%
Routed	V2	0.00		0.0		0.00		0.00				100%				100%
												100%				100%
Deployment	V2	x		x				#VALUE!				100%				100%
Upgrade Software	V2	0.00		0.0		0.00		0.00				100%				100%
Upgrade Datebase	V2	0.00		0.0		0.00		0.00				100%				100%
Test Itamae	V2	0.00		0.0		0.00		0.00				100%				100%
												100%				100%
Promotion	V2	x		x				#VALUE!				100%				100%
Developer Education	V2	x		x				#VALUE!				100%				100%
Vim IDE	V2	0.00		0.0		0.00		0.00				100%		incl. Bash scripts		100%
Database model	V2	0.00		0.0		0.00		0.00				100%				100%
New Project Layouts	V2	0.00		0.0		0.00		0.00				100%				100%
Community Education	V2	x		x				#VALUE!				100%				100%
Social Media	V2	0.00		0.0		0.00		0.00				100%				100%
Bike Shop Flyers	V2	0.00		0.0		0.00		0.00				100%				100%
MetC User Forum	V2	x		x				#VALUE!				100%				100%
Presentation Preparation	V2	0.00		0.0		0.00		0.00				100%				100%
Presentation Presentation	V2	0.00		0.0		0.00		0.00				100%				100%

## Scratch
-100%	-100%
0%	0%
5%	5%
10%	10%
15%	15%
20%	20%
25%	25%
30%	30%
35%	35%
45%	45%
50%	50%
55%	55%
60%	60%
65%	65%
70%	70%
75%	75%
80%	80%
85%	85%
90%	90%
95%	95%
100%	100%
101%	101%